## Dark
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2022-03-11 |  |  |  |  | March | [20 empty] | April | [27 empty] | May
Scrolling Increment: | 3 | time axis 2022-03-14 to 2022-05-08
Milestone description | Category | Assigned to | Progress | Start | Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Iteration 1
Group meeting report template | On Track | Carl Inguanzo | 100% | 2022-03-11 | 3
Stakeholder Register | On Track | Carl Inguanzo | 100% | 2022-03-16 | 1
Personas | Low Risk | All member | 100% | 2022-03-08 | 10
Final Impressions | Med Risk | All member | 100% | 2022-03-31 | 1
Readme.md/Wiki page | Milestone | Matthew Harris | 100% | 2022-03-17 | 6 | bar: T to T
Iteration 2
Create a Gantt chart | On Track | Carl Inguanzo | 75% | 2022-04-02 | 13
Resources requirement register | On Track | All member | 100% | 2022-04-25 | 9
Test and Review new changes | On Track | All member | 100% | 2022-05-20 | 11
Group meeting report template | On Track | Matthew Harris | 100% | 2022-05-22 | 1
Stakeholder Register | On Track | Carl Inguanzo | 100% | 2022-05-23 | 24
Interation 3
Group meeting report template | On Track | Matthew Harris | 100% | 2022-03-26 | 4
Risk Register | On Track | Carl Inguanzo | 100% | 2022-03-29 | 14
Pushed | Low Risk | All member | 100% | 2022-04-13 | 6
publish | Med Risk | Matthew Harris | 100% | 2022-06-13 | 3
User Acceptance Test Restults Templates | Low Risk |  |  | 2022-03-17 | 19
TITLE 4
Task 1 |  |  |  | 2022-06-16 | 15
Task 2 |  |  |  | 2022-06-30 | 5
Task 3 | Milestone |  |  | 2022-08-11 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Light
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2022-05-30 |  |  |  |  | May | [6 empty] | June | [27 empty] | July
Scrolling Increment: | 1 | time axis 2022-05-31 to 2022-07-25
Milestone description | Category | Assigned to | Progress | Start | Days | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M
TITLE 1
Task 1 | Goal | Name | 25% | 2022-05-30 | 3 | T: 2; W: 2
Task 2 | Milestone |  |  | 2022-06-04 | 1 | bar: S
Task 3 | Low Risk |  | 50% | 2022-05-27 | 10
Task 4 | Milestone |  |  | 2022-06-19 | 1 | bar: S
Task 5 | Med Risk |  | 10% | 2022-06-05 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2022-06-05 | 13
Task 2 | On Track |  | 50% | 2022-06-07 | 9
Task 3 | Low Risk |  | 33% | 2022-06-12 | 11
Task 4 | Milestone |  |  | 2022-06-14 | 1 | bar: T
Task 5 |  |  |  | 2022-06-15 | 24
TITLE 3
Task 1 | On Track |  |  | 2022-06-14 | 4
Task 2 | Med Risk |  |  | 2022-06-17 | 14
Task 3 | On Track |  |  | 2022-07-02 | 6
Task 4 | Goal |  |  | 2022-07-06 | 3 | W: 2; T: 2; F: 2
Task 5 | Low Risk |  |  | 2022-06-05 | 19
TITLE 4
Task 1 |  |  |  | 2022-07-09 | 15
Task 2 |  |  |  | 2022-07-23 | 5
Task 3 | Milestone |  |  | 2022-09-03 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Color
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2022-05-30 |  |  |  |  | June | [27 empty] | July
Scrolling Increment: | 5 | time axis 2022-06-04 to 2022-07-29
Milestone description | Category | Assigned to | Progress | Start | Days | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
TITLE 1
Task 1 | Goal | Name | 25% | 2022-05-30 | 3
Task 2 | Milestone |  |  | 2022-06-04 | 1 | bar: S
Task 3 | Low Risk |  | 50% | 2022-05-27 | 10
Task 4 | Milestone |  |  | 2022-06-19 | 1 | bar: S
Task 5 | Med Risk |  | 10% | 2022-06-05 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2022-06-05 | 13
Task 2 | On Track |  | 50% | 2022-06-07 | 9
Task 3 | Low Risk |  | 33% | 2022-06-12 | 11
Task 4 | Milestone |  |  | 2022-06-14 | 1 | bar: T
Task 5 |  |  |  | 2022-06-15 | 24
TITLE 3
Task 1 | On Track |  |  | 2022-06-14 | 4
Task 2 | Med Risk |  |  | 2022-06-17 | 14
Task 3 | On Track |  |  | 2022-07-02 | 6
Task 4 | Goal |  |  | 2022-07-06 | 3 | W: 2; T: 2; F: 2
Task 5 | Low Risk |  |  | 2022-06-05 | 19
TITLE 4
Task 1 |  |  |  | 2022-07-09 | 15
Task 2 |  |  |  | 2022-07-23 | 5
Task 3 | Milestone |  |  | 2022-09-03 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one